# Project Meridian — Project Charter (Excerpt)

Document: Project Charter v1.2 — Section 7 extract

Sponsor: Marcus Alvarez, Chief Operating Officer

Programme: CRM Modernisation

# 7. Initial Risk Assessment

At charter approval the steering committee recorded the following strategic risks to be actively managed by the programme. These are reviewed at each stage gate.

Strategic risk SR-01 (Executive sponsorship continuity). The cause is a pending reorganisation of the operations division. The event is loss of an engaged executive sponsor mid-programme; the effect is stalled decisions and funding uncertainty. Owner: Marcus Alvarez (COO). Response: name a deputy sponsor with delegated authority. Status: open.

Strategic risk SR-02 (Regulatory approval). Brightline operates in a regulated insurance market; the cloud platform must pass an information-security assessment before holding customer data. If approval is delayed, the event is a blocked production cutover, with the effect of a schedule slip beyond the 24-week window. Likelihood Low, impact High. Owner: Sade Okafor (Security Lead). Response: engage the regulator early and book the assessment in Week 14. Status: open.

Strategic risk SR-03 (Legacy decommission dependency). The legacy CRM also feeds the nightly actuarial reporting batch. The cause is a hidden downstream dependency; the event is that decommissioning legacy breaks actuarial reporting; the effect is a gap in regulatory financial reporting. Likelihood Medium, impact High. Owner: Priya Nair (Data Lead). Response: map and re-point the downstream feed before decommission. Status: open.