# Risk Register

Project: Project Meridian

Date: Week 9, Thursday

| Risk ID | Cause | Event | Effect | P | I | Score | Response | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M-01 |  |  |  | High | High |  | A deterministic de-duplication pass plus a validation gate that blocks migration if the duplicate rate exceeds 0.5%. | Priya Nair (Data Lead) | in progress |
| M-02 | The contract for the third-party policy-rating API has not been finalised by the vendor, Acme Ratings Ltd. | Integration testing in Week 13 cannot start on time. | A direct slip to the UAT entry date. | Medium | High |  | Escalate to vendor account management and prepare a stub-based fallback so internal testing is not blocked. | Tom Becker (Integration Lead) | open and escalating |
| M-03 | An unresolved allocation conflict (two senior engineers shared 50/50 with the parallel Billing programme). | Reduced migration throughput. | A potential two-week schedule slip. | Medium | Medium |  | A dedicated-allocation request has been submitted to the resourcing board. | Dana Whitfield (PM) | mitigating |
| SR-01 | An unengaged executive sponsor mid-programme. |  | Stalled decisions and funding uncertainty. |  |  |  | Name a deputy sponsor with delegated authority. | Marcus Alvarez (COO) | open |
| SR-02 | Brightline operates in a regulated insurance market; the cloud platform must pass an information-security assessment before holding customer data, and approval may be delayed. | A blocked production cutover. | A schedule slip beyond the 24-week window. | Low | High |  | Engage the regulator early and book the assessment in Week 14. | Sade Okafor (Security Lead) | open |
| SR-03 | A hidden downstream dependency (the legacy CRM also feeds the nightly actuarial reporting batch). | Decommissioning legacy breaks actuarial reporting. | A gap in regulatory financial reporting. | Medium | High |  | Map and re-point the downstream feed before decommission. | Priya Nair (Data Lead) | open |